## Sheet1
Bug sheet
PAGE NAME | ISSUE ID | ISSUE NAME | DESCRIPTION | REFERENCE(IMAGE/VIDEO) LINK | BUG TYPE/CATEGORY | PRIORITY/SEVERITY | STATUS | IMPACT | ASSIGNEE | DATE ASSIGNED
HOME PAGE | 1 | Alignment Issue | The alignment of the widget is not scaled properly | https://prnt.sc/rE6UeW1VA3F1 | UI | MEDIUM | Open | MEDIUM |  | 2023-02-11
| 2 | Subscription email input box | The mail input box instead of one there are two input boxes of mail Also there's no placeholder text to indicate the expected format or content that should be entered into the input field | https://prnt.sc/tjKskFLyZbTb | Functional | HIGH | Open | HIGH |  | 2023-02-11
| 3 | Scroll to top button | The Scroll to top button is not placed properly as it was there behind the HELP button | https://prnt.sc/Odu2hgB-DjMj | UI | HIGH | Open | HIGH |  | 2023-02-11
| 4 | Unwanted text in Header(all pages) | Whenever while navigating , There's an text-"Trustpilot" appears in the header | https://prnt.sc/1JrbltfsUx1N | UI | MEDIUM | Open | MEDIUM |  | 2023-02-11
| 5 | Signing up newsletter text | After signed up newsletter, the message appears seems to be not aligned properly | https://prnt.sc/Pujw6VpTWjcJ | UI | LOW | Open | LOW |  | 2023-02-11
Laptop Page | 6 | Laptop filter | Laptop filter is unnnecessary as the page itself dedicated to laptop alone | https://prnt.sc/eKuKuSZQ4x9J | Functional | HIGH | Open | HIGH |  | 2023-02-11
| 7 | RAM and displayFilter not working | The filter is not working and the page also get refreshed |  | Functional | HIGH | Open | HIGH |  | 2023-02-11
| 8 | Unwanted filter in Touchscreen Filter | There is another selection button in Touchscreen called "N"which is unwanted | https://prnt.sc/yB9qHy5Gdll- | Functional | HIGH | Open | HIGH |  | 2023-02-11
| 9 | Navigating to Compare page | After adding 2 or more products, the added tag is not changed to "Go to compare " page which makes the user diificult to find the page. | https://prnt.sc/7e68llATRB8h | UI | HIGH | Open | HIGH |  | 2023-02-11
| 10 | Space Issue | There's an lot of space in the product detail page, which can be reduced for better user experience | https://prnt.sc/Cb2OIWuD4AZm | UI | MEDIUM | Open | MEDIUM |  | 2023-02-11
| 11 | Close button-product overview | after opening the image of the product, there's no close button provided | https://prnt.sc/FNUPj3cdxufN | UI | HIGH | Open | HIGH |  | 2023-02-11
Smartphones | 12 | Unwanted filter | There's an filter called "Port" which has no functionality with that | https://prnt.sc/05RW8-ILBCLv | UI | HIGH | Open | HIGH |  | 2023-02-11
| 13 | Filter Issue | There is another selection button in Touchscreen called "Y"which has no proper functionality | https://prnt.sc/66FP3kBfN4Ke | Functional | HIGH | Open | HIGH |  | 2023-02-11
|  | Empty spaces in Spec area | For some models, there's no specs provided in the main page | https://prnt.sc/Tx-3qrlXhUL2 | UI | HIGH | Open | HIGH |  | 2023-02-11
Refurbished IPhones | 14 | Alignment and resizing issues | The space is not aligned propely | https://prnt.sc/DeWZFnqM6TNT | UI | HIGH | Open | HIGH |  | 2023-02-11
Printing &Services | 15 | Unresponsive Buttons | Unlike other pages, We are unable to redirect to printing and services by clicking the respective button in the header bar | https://drive.google.com/file/d/1STSm_aijqHxS_DIPPp3bP0Gi_JNKgmtC/view?usp=sharing | Functional | HIGH | Open | HIGH |  | 2023-02-11
Sevices Page | 16 | Page error | If we chose Ipad services and then selected the model, the page was throwing 404 error | https://prnt.sc/5FEZIq8rRITf | Functional | HIGH | Open | HIGH |  | 2023-02-11
Tablet page | 17 | Improper spec details | The specs were not properly given for some products | https://prnt.sc/cUSy0TA7SUnd | UI | HIGH | Open | HIGH |  | 2023-02-11
My Account | 18 | Loggin error | Even after logging in ..can't find my account in my account page and it still asks to register |  | Functional | HIGH | Open | HIGH |  | 2023-02-11
Services page | 19 | Service page issue | By clicking the repairservices banner in the home page, it re-directs to page called Services which is not accesible | https://drive.google.com/file/d/1Ie-9S74Lj2HwJOMQBOBxw-aSLhPAFGFY/view?usp=drive_link | Functional | HIGH | Open | HIGH |  | 2023-02-11
All pages | 20 | Image loading Issue | In certain page, the truspilot image is not loaded properly | https://prnt.sc/zsJuk8a8pmpc | UI | LOW | Open | LOW |  | 2023-02-11
Help Button | 21 | Help Button | Even after closing the chatbot chat, the details were not cleared | https://prnt.sc/Btza3aZIKV0h | UI | LOW | Open | LOW |  | 2023-02-11